| Project components | Outputs | Activities | Institution Responsible | Activity total | Output total | Component total | Grand total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Project grand total to be budgeted 19/12/24 |  |  |  |  |  |  | 2,030,291 |
| PC1: Gender Responsive Climate Change Adaptation (CCA) measures mainstreamed into relevant sector policies and national strategy. PC 1 Total |  |  |  |  |  | 200,000 |  |
|  | O1.1. Recommendations developed through private sector engagement for mainstreaming gender responsive CCA into sectoral/coastal fisheries value chain-related policies and strategies O 1.1 Total |  |  |  | 38,000 |  |  |
|  |  | 1.1.1 Identify the gaps in the relevant policies and strategies (energy, fisheries, agriculture, gender, etc. | MoFWR/DoF (Sub-contract | 12,000 |  |  |  |
|  |  | 1.1. 2 Adapt relevant policies & strategies to include CCA & gender mainstreaming in fisheries value chain. | MoFWR/DoF and Climate Change Office | 14,000 |  |  |  |
|  |  | 1.1.3 Create an umbrella association of all key private sector players of the fisheries value chain for advocacy and coordination purposes. | MoFWR/DoF | 4,000 |  |  |  |
|  |  | 1.1.4 Organize a validation workshop on the recommended policies & strategies adaptations | MoFWR/DoF | 8,000 |  |  |  |
|  | O1.2. Climate resilient business model for fisheries waste management and processing developed and demonstrated for private/public uptake O 1.2 Total |  |  |  | 63,000 |  |  |
|  |  | 1.2.1. Stakeholder mapping of fish processing enterprises including fisheries waste types and potential uses | MoFWR/DoF | 5,000 |  |  |  |
|  |  | 1.2.2. Promote the establishment of climate resilient facilities and processes for efficient recovery and production of value added and usable product. | MoFWR/DoF | 20,000 |  |  |  |
|  |  | 1.2.3. Conduct studies on the market potential for processed fish waste alternatives | MoFWR/DoF | 8,000 |  |  |  |
|  |  | 1.2.4. Develop a waste collection system, including the required logistics, and processing unit(s) as part of pilot project | Empass, bsc feed (sub-contract) & masannah ceesay fish & vegetable enterprise | 30,000 |  |  |  |
|  | O1.3. The staff of DoF, local government, environmental and business sector regulators, industries and cooperatives trained on gender responsive climate- resilient adaptation measures, supporting the integration of CCA into fisheries value chain development O 1.3 Total |  |  |  | 99,000 |  |  |
|  |  | 1.3.1. Identify capacity and knowledge gaps of targeted stakeholders. | MoFWR/DoF (sub-con | 10,000 |  |  |  |
|  |  | 1.3.2. Design relevant training materials on climate resilient and gender equality for adaptation measures. | Directorate of Gender + Climate Change Directorate (Sub-contract) | 25,000 |  |  |  |
|  |  | 1.3.3 Provide training and capacity building activities, including in collaboration with co-financing partner programme institutions and specialized institutions | MoTIE (GIEPA,GCCI) Sub-Contract | 34,000 |  |  |  |
|  |  | 1.3.4. Develop and provide support services for value addition and export trade (feasibility study for the inclusion of services - such as ice facility generation, ice provision facility etc). | MOFWR/DOF, FSQA | 30,000 |  |  |  |
| PC2: Resilience building models for small scale fisheries-dependent enterprises and populated coastal communities PC 2 Total |  |  |  |  |  | 1,369,000 |  |
|  | O2.1. Innovative climate-proof post-harvest technologies implemented at three Community Fisheries Centers (CFCs), with capacity building O 2.1 Total |  |  |  | 906,000 |  |  |
|  |  | 2.1.1. Conduct need assessment on capacity and knowledge gaps of project implementing partners | MoFWR/DoF and GTTI (Sub-contract) | 30,000 |  |  |  |
|  |  | 2.1.2 Undertake in-depth needs assessment and develop plans for addressing post-harvest issues with project implementing partners. | MoFWR/DoF and GTTI (Sub-contract) | 35,000 |  |  |  |
|  |  | 2.1.3 Developing Training packages that incorporate good practices for containment and recovery responses to the covid-19 pandemic. | MoFWR/DoF and GTTI (Sub-contract) | 0 |  |  |  |
|  |  | 2.1.4 Build fish processing and handling facilities at three community fisheries centres for fish processors with the accompanying logistics and raise awareness on these pilot projects in the 3 CFCs. | MoFWR/DoF and GTTI (Sub-contract) | 841,000 |  |  |  |
|  | O2.2. Business service providers trained to train enterprises on business skills and innovative climate- resilient strategies for value added fish storage and processing O 2.2 Total |  |  |  | 310,000 |  |  |
|  |  | 2.2.1 Select the business service providers (from the fish processing units identified) and train them on how to mainstream CC adaptation and to develop the skills training plan | MoFWR/DoF, GTTI, GIEPA (Sub-contract) | 60,000 |  |  |  |
|  |  | 2.2.2. Identify capacity and knowledge gaps of enterprises. | MoFWR/DoF, GCCI, GIEPA (Sub-contract) | 30,000 |  |  |  |
|  |  | 2.2.3 Design relevant training materials on business skills and innovative strategies for value-added fish processing and export trade (to be conducted in parallel with 1.3.2). | MoFWR/DoF, GCCI, GIEPA,FSQA (Sub-contract) | 40,000 |  |  |  |
|  |  | 2.2.4 Conduct businesses skill training for 45 businesses in the fisheries sector |  | 180,000 |  |  |  |
|  | O2.3. Climate resilient business plans developed by selected enterprises O 2.3 Total |  |  |  | 153,000 |  |  |
|  |  | 2.3.1 Develops clear selection criteria for selected enterprises. | MoFWR/DoF & GTTI (Sub-contract) | 22,000 |  |  |  |
|  |  | 2.3.2. Develop climate resilient business plans for selected enterprises. |  | 33,000 |  |  |  |
|  |  | 2.3.3 Identify selected climate resilient business plans developed by selected enterprises | MoFWR/DoF &GTTI (Sub-contract) | 8,000 |  |  |  |
|  |  | 2.3.4 Provide technical assistance on integrating climate resilience in business plans and updating feasibility assessments to selected enterprises. | MoFWR/ GEIPA,GCCI | 90,000 |  |  |  |
| PC 3: Community empowerment and awareness raising on CCA in fisheries value chains PC 3 Total |  |  |  |  |  | 300,000 | 0 |
|  | O3.1. Plan for public awareness campaigns Implemented to enhance communication and dialogue on CC impacts on coastal fisheries livelihoods O3.1 Total |  |  |  | 80,000 |  |  |
|  |  | 3.1.1. Design the materials for public awareness-raising campaigns taking account of existing campaigns and keep updating them. | Directorate of Climate Change/DWR/MoFWR-DoF | 30,000 |  |  |  |
|  |  | 3.1.2. Roll-out public awareness campaigns. | MoFWR/DoF | 50,000 |  |  |  |
|  | O3.2. Training materials to introduce climate adaptation solutions in the coastal fisheries sector developed and resilience capacity building workshops held for selected CFCs and educational institutions O 3.2 Total |  |  |  | 100,000 |  |  |
|  |  | 3.2.1. Design relevant training materials on introducing climate adaptation solutions in the coastal fisheries sector. | Directorate of Climate Change/DWR/MoFWR/DoF | 40,000 |  |  |  |
|  |  | 3.2.2. Conduct training and workshop on introducing climate adaptation solutions in the coastal fisheries sector. | Directorate of Climate Change/DWR/MoFWR/DoF | 60,000 |  |  |  |
|  | O3.3. Lessons learned documented and disseminated to relevant audiences, with support for regional uptake, replication and scaled up investment O3.3. Total |  |  |  | 120,000 |  |  |
|  |  | 3.3.1. Catalogue success stories, challenges and solutions, by periodic monitoring. | MoFWR/DoF | 88,000 |  |  |  |
|  |  | 3.3.2. Disseminate lessons learnt and best practice | MoFWR/ Communication Unit | 32,000 |  |  |  |
| PC4 - Project Monitoring & Evaluation PC4 Total |  |  |  |  |  | 161,291 | - |
|  | O4.1: Project monitoring | 4.1.1 PeMU running | MoFWR/DoF | 91,180 |  |  |  |
|  |  | 4.1.2 1st PSC meeting & 2nd PSC meeting | MoFWR/DoF | 1,500 |  |  |  |
|  |  | 4.1.3 3rd and 4th PSC meeting | MoFWR/DoF | 1,500 |  |  |  |
|  |  | 4.1.4 5th and 6th PSC meeting | MoFWR/DoF | 1,500 |  |  |  |
|  |  | 4.1.5 7th PSC meeting | MoFWR/DoF | 750 |  |  |  |
|  |  | 4.1.4 Progress report submitted to UNIDO HQ ( 4 times) | MoFWR/DoF | 4,000 |  |  |  |
|  |  | 4.1.5 Submission of PIRs, Mid term and Final evaluation, etc | UNIDO | 15,600 |  |  |  |
|  |  |  | UNIDO | 15,000 |  |  |  |
|  |  |  | UNIDO | 30,261 |  |  |  |
| grand total | grand total | grand total |  |  |  |  | 2,030,291 |